## Slide 1: Allied World Vault Lauch Plan
Allied World Assurance Compan (AWAC) - Vault
Sept 2019
Notes: New tech paradigm: truly distributed computing, cloud native, microservices; nobody else has it, it is real and a generation ahead of others, and it is necessary for digital era to enable massive volume, variation, velocity
New business model: instead of trying to replace the core of all insurers in the world, we will primarily offer this new tech as PaaS to enable others to build apps, and build contents, connectivity to both insurers and channels/affinities
Next steps with Verisk: what are the immediate next steps to move this forward with small investment and superfast benefits realized for both sides, one to two months to see business values, not POC and big decision making

## Slide 2: Agenda
© 2019 eBaoTech Corporation. All rights reserved.
In order to launch there are 5 tracks of work that need to be addressed - 3 “internal” tracks and 2 standard project launch tracks
  INTERNAL
  #1 –Claim v4.5 Framework
  #2 – Thread UX API’s thru InsureMO
  #3 – Claim UX code clean up
  STANDARD
  #4 – Create Final Vault Project Plan Proposal
  #5 – Project Readines - Internal Set Up
Ramp a combined team across U.S. / China / India (Martin, Mark & Baton)
  Plan and budget for 2 to 3 key FTE from India to go to China for knowledge training (i.e. Anshul, Subrashee & Prolok)
Complete the final commercials (Randy, Martin & Baton)
  PaaS / SaaS Financials
  Vault Claim Project Financials
  Legal Documents (MSA / SaaS/PaaS Work Order / Project Work Order)
Complete the project plan and proposal for Vault Insurance (Mark, Ivy & Team)
  Scope & Timeline
Notes: Evolution of the industry
We have moved from enterprise application company to Insurance PaaS company.
We are rare vendor that do “everything”
Where we are going is based on future state of the industry and customer markets
i.e. better aligned with cloud practices
expand our PaaS offering to the global market

## Slide 3: Pre Launch Tracks
© 2018 eBaoTech Corporation. All rights reserved.
Track | Description | Resources | Other
#1 –Claim v4.5 Framework | Move v4.2 “Trust” Version into v4.5 Framework, with the whole v4.2 Claim as a single microservice managed by v4.5 microservice infrastructure. Further split of v4.2 claim into smaller microservices would be in future. No multi-tenant / function / configuration changes. | PBU – Alfonso / Yi Feng Zhongbiao (AD) | TBD
#2 – Thread UX thru InsureMO API’s | Identify and register all claim API’s in InsureMO (backend work) Thread the Claim UX API’s thru the InsureMO cloud container (UI code work) | PBU / Zhongbiao (AD) UI resource (?) Testing – Shureesha & Jothi Pune | TBD
#3 – Claim UX code clean up | Clean up existing code in UX so that it can be handed over to AWAC Vault AD’s The clean-up criteria and tasks would need to be defined by ourselves, with unit tests as one of must-have items There is no intension to re-write or make fundamental changes to code logic or technology stack | TBD , Prolok Testing – TBD | TBD
#4 – Create Final Vault Project Plan Proposal | Based on Discover Workshop – create a project plan and proposal | Mark, Ivy Cheng, Fei Lu | TBD
#5 – Project Readines - Internal Set Up | Identify testing strategy that aligns with the project approach and our delivery responsibilities Set up internal Dev, Test etc environments Set up Testing Automation and Frameworks Set up automated build & deploys | Sachin, Fei Lu | 
Notes: New tech paradigm: truly distributed computing, cloud native, microservices; nobody else has it, it is real and a generation ahead of others, and it is necessary for digital era to enable massive volume, variation, velocity
New business model: instead of trying to replace the core of all insurers in the world, we will primarily offer this new tech as PaaS to enable others to build apps, and build contents, connectivity to both insurers and channels/affinities
Next steps with Verisk: what are the immediate next steps to move this forward with small investment and superfast benefits realized for both sides, one to two months to see business values, not POC and big decision making

## Slide 4: Notes on Task #2: Thread UX thru InsureMO API’s
Status
  Videos to help understand:
    https://drive.google.com/open?id=1Vn2BVSkstkeGFarH3B_ItyMdQCwgUITn
    https://drive.google.com/open?id=1KRdSg2KpfXZxE11V0zMcO2QGektmnIyw
    https://drive.google.com/open?id=1_NzRYaucfx4mzv5lyd_S2F_jPPPWSLBI
  We do NOT have a list of APIs. Nobody have them (@9/5/2019).We have to manage to find them out.
  As part of effort of Task #1 (drop Trust Claim into v4.5 microservice structure), we will refactor the system in a way that we would be able to adopt some tool to automatically extract swagger files from system, so that we could conduct Task #2, e.g., register them in eBaoCloud Container.
  HOWEVER there will be 3 pending tasks after the automatic extraction of API swagger files:
    review each one and UI code to make sure it is actually called by UI directly or indirectly;
    clean up and add human-written description to generated swagger files;
    manually test each one to make sure it actually works.
  These 3 tasks, as you could immediately figure out, take a lot, or huge, of effort and are not so urgent so we might not do them immediately.
  Having said this, we might still choose some more important APIs to do these 3 tasks, for demo purpose only.
  If we conduct above action, which is a question mark, APIs we would select would be the first batch of APIs. It is still undecided which APIs we would select and this action might not be taken at all since this has not impact to Vault delivery.
Test
  So do not expect we would have robust API list and document available. We probably will not have them even to the end of this project and even longer.
  Maybe one way to test API is to walk through the UI as in a manual test case, collect API calls along the way using Chrome DevTools and put them down. Another benefit of this approach is to collect request data also along the way. Actually this was exactly how PBU testers managed to test Policy Admin APIs.
  Of course, an even better way is to automatically do this. Not sure whether below is helpful.
    https://learning.getpostman.com/docs/postman/sending_api_requests/capturing_http_requests/
Issues
  Performance
    We are required to direct API calls from UI to eBaoCloud Container installed in EU which in turn calls Claim installed in AWS in US
    The price for hosting does not include eBaoCloud Container and hence we are reusing EU eBaoCloud Container instance. There is another one in SG but that is even slower.
    Austin Huang is going to conduct some network latency test with help from Ismael to find out whether the latency is acceptable or now.

## Slide 5: Notes on Task #3: Claim UX code clean up
Clean up scope and approach is in a separate PPT
It will be a cut-over. Once, at some time point likely mid Oct, we delivery UI source code to Vault, we are not going to touch UI code any more. We would only focus on APIs.
On the other side, we need to be prepared to get Vault IT up to speed and support them to change UI code along the way, e.g., provide training and ongoing support services.
Resource-wise:
  Zhongbiao is not working on UI clean up. He is working on Task #1
  We might get Vincent Zhao to lead this as suggested by PBU.
  Although we are still working on defining goals and estimating efforts, one resource is definitely not enough. Sachin is proposing Jasmine/karma
  Skillset-wise, JavaScript and React are a must.

## Slide 6: Plan for Task #3
Date | Task
~ 9/10 | Get Claim UI code extracted and up and running [AH@9/10] Done by Feng Yi
~ 9/20 | Unit Test Cases Phase 1# (end-to-end test), incl. mock-up setup
~ 9/11 | UI Code clean-up approach and estimation
9/12 ~ | UI code clean-up – structure level
9/12 ~ | UI code clean-up – file level
9/20 ~ | Unit Test Cases cont. (optional, depending on code coverage achieved on Phase 1#)
9/12 ~ | Documentation (in-code comments, README, tutorials, etc.)

## Slide 7: Pre Launch & Program Summary Timeline
TBD – please put activities and date targets (AH@[9/5] Refer to next slide)
Daily Status
© 2018 eBaoTech Corporation. All rights reserved.
Track 1 Status
(Austin & Yi Feng)
API’s Register & Thread to InsureMO
(Austin, Yi, Sachin)
TBD – please put activities and date targets
Establish testing (Junit / Functional etc.) (Sachin)
Zhongbiao (AD)
Subrashee (AD)
UX Code Clean Up
(OWNER TBD)
TBD – please put activities and date targets (AH@[9/5] Refer to next slide)
What is first batch of API’s registered (Austin & Yi Fend) (AH@[9/5] Refer to slide 4, last bullet point of “Status” section)
Establish testing (Junit / Functional etc.) (Sachin) (AH@[9/5] Refer to slide 4, “Test” section)
Update regularly
Notes: New tech paradigm: truly distributed computing, cloud native, microservices; nobody else has it, it is real and a generation ahead of others, and it is necessary for digital era to enable massive volume, variation, velocity
New business model: instead of trying to replace the core of all insurers in the world, we will primarily offer this new tech as PaaS to enable others to build apps, and build contents, connectivity to both insurers and channels/affinities
Next steps with Verisk: what are the immediate next steps to move this forward with small investment and superfast benefits realized for both sides, one to two months to see business values, not POC and big decision making

## Slide 8: Task #1 & #2 Tracking
Managed by PBU; Zhongbiao works for PBU
Date | Task
Sep 5th -6th | Carve Claim app out of Trust; [AH@9/10] Done. Microservice refactor (introduce Springboot/SpringCloud)
Sep 9th -13th | Microservice refactor (introduce Springboot/SpringCloud) cont. [AH@9/10] Ongoing. Challenging but not so risky. PBU is fully on it, supporting Zhongbiao.
Sep 16th – 20th | Microservice functional working TS deployment process working replace CAS
Sep 23th – 30th | ES/MQ middleware replacement
Oct 8th – 18th (Track #2) | Stabilization extract Claim API Swagger register to Container replace UI API call URLs to reverse proxy from Container
Note:
Vault project kick off is not dependent on completion of tasks in this slide, since they deal with different part of the code.
Track #2 is after Track #1.The last line in below table refers Track #2 and the first 4 lines for Track #1.

## Slide 9: Pre Launch & Program Summary Timeline
Pre Launch Tasks – See pre launch plan
Negotiate final PaaS commercial – sign SOW
Agreed on Vault Scope for Day 1 Go LIve
Negotiate first implementation – sign SOW for Day 1 scope
Assemble team and get going
© 2018 eBaoTech Corporation. All rights reserved.
September
October
Target Go Live Mid March or earlier 2020 for “Day 1”
TBD scope and release date for “Day 2” scope
Nov thru Mar 2020
Target contract effective date October 1
First real sprint start October 7th or 14th
Notes: New tech paradigm: truly distributed computing, cloud native, microservices; nobody else has it, it is real and a generation ahead of others, and it is necessary for digital era to enable massive volume, variation, velocity
New business model: instead of trying to replace the core of all insurers in the world, we will primarily offer this new tech as PaaS to enable others to build apps, and build contents, connectivity to both insurers and channels/affinities
Next steps with Verisk: what are the immediate next steps to move this forward with small investment and superfast benefits realized for both sides, one to two months to see business values, not POC and big decision making